## Cover Page
AI Course
Capstone Project
Work Breakdown Structure
For students
ⓒ2023 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung Innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today |  |  | 2025-12-05
Project Team Name |  |  | رنان - Rannan
Project Topic |  |  | The lingustic advisor
Task |  |  |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4
[9 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20
[9 empty] | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04
1. The lingustic advisor project |  |  |  | 2025-11-09 | 2025-12-06 |  |  | Done
| 1.1. Project Initiation |  |  | 2025-11-09 | 2025-11-16 |  |  | Done | bar: 2025-11-09 to 2025-11-16
|  | 1.1.1. Select final project idea |  | 2025-11-09 | 2025-11-09 |  |  | Done | bar: 2025-11-09
|  | 1.1.2. Prepare and submit Action Plan draft |  | 2025-11-10 | 2025-11-16 |  |  | Done | bar: 2025-11-10 to 2025-11-16
| 1.2. Data Preparation |  |  | 2025-11-16 | 2025-11-22 | bar: 2025-11-16 to 2025-11-20
|  | 1.2.1. Collect the data |  | 2025-11-17 | 2025-11-19 |  |  | Done | bar: 2025-11-17 to 2025-11-19
|  | 1.2.2. Clean the data |  | 2025-11-19 | 2025-11-20 |  |  | Done | bar: 2025-11-19 to 2025-11-20
|  | 1.2.3. Preprocess the data |  | 2025-11-20 | 2025-11-22 |  |  | Done | bar: 2025-11-20
| 1.3. Retrieval System Development |  |  | 2025-11-23 | 2025-12-29 |  |  | Done | bar: 2025-11-23 to 2025-11-27
|  | 1.3.1. Develop and implement a retrieval system |  | 2025-11-23 | 2025-12-29 |  |  | Done | bar: 2025-11-23 to 2025-11-27
| 1.4. Backend Development |  |  | 2025-11-30 | 2025-12-05 |  |  | Done | bar: 2025-11-30 to 2025-12-04
|  | 1.4.1. Select backend implementation tools |  | 2025-11-30 | 2025-12-05 |  |  | Done | bar: 2025-11-30 to 2025-12-04
|  | 1.4.2. Start implementation and development |  | 2025-11-30 | 2025-12-05 |  |  | Done | bar: 2025-11-30 to 2025-12-04
| 1.5. Frontend Development |  |  | 2025-11-30 | 2025-12-05 |  |  | Done | bar: 2025-11-30 to 2025-12-04
|  | 1.5.1. Build frontend prototype |  | 2025-11-30 | 2025-12-05 |  |  | Done | bar: 2025-11-30 to 2025-12-04
|  | 1.5.2. Select frontend implementation tools |  | 2025-11-30 | 2025-12-05 |  |  | Done | bar: 2025-11-30 to 2025-12-04
|  | 1.5.3. Start implementation and development |  | 2025-11-30 | 2025-12-05 |  |  | Done | bar: 2025-11-30 to 2025-12-04
| 1.6. Testing |  |  | 2025-11-30 | 2025-12-05 |  |  | Done | bar: 2025-11-30 to 2025-12-04
|  | 1.6.1. Select testing groups |  | 2025-11-30 | 2025-12-05 |  |  | Done | bar: 2025-11-30 to 2025-12-04
|  | 1.6.2. Preform testing |  | 2025-11-30 | 2025-12-05 |  |  | Done | bar: 2025-11-30 to 2025-12-04
| 1.7. Documentation & Presentation |  |  | 2025-11-30 | 2025-12-05 |  |  | Done | bar: 2025-11-30 to 2025-12-04
|  | 1.7.1. Finalize project documentation |  | 2025-11-30 | 2025-12-05 |  |  | Done | bar: 2025-11-30 to 2025-12-04
|  | 1.7.2. Finalize project presntation |  | 2025-11-30 | 2025-12-05 |  |  | Done | bar: 2025-11-30 to 2025-12-04
|  | 1.7.3. Present the project |  | 2025-11-30 | 2025-12-05 |  |  | Done | bar: 2025-11-30 to 2025-12-04